## PTWS ACTION MONITOR
ACTION CODE | ACTION DESCRIPTION | REFERENCE | LEAD | DEADLINE | COMPLETION | STATUS | COMMENTS
P-2023-09-01 | PacWave24 will be announced by Circular Letter from the IOC to Member States before 31 January 2024 | ICG/PTWS-XXX | TT-PW/Sec | 2024-01 | 2024-05 | COMPLETED | PacWave 24 was announced by CL-2999 dated on 28 May 2024.
P-2023-09-02 | PacWave24 Manual to be distributed by the IOC to Member States before 30 April 2024 | ICG/PTWS-XXX | TT-PW/Sec | 2024-01 | 2024-05 | COMPLETED | PacWave24 Manual was attached to the CL-2999.
P-2023-09-03 | Participating Member States are requested to complete and submit PacWave24 Exercise Evaluation Survey online by 15 December 2024 to complete (National/Exercise Survey + Live TSP Communications Test evaluation survey). | ICG/PTWS-XXX | TT-PW | 2024-12 | 2024-12-01 | COMPLETED
P-2023-09-04 | PacWave24 TSPs live communication test, 05 November 2024, 00:00 UTC | ICG/PTWS-XXX | CATAC, NWPTAC, PTWC, SCSTAC | 2024-11 | 2024-11-01 | COMPLETED
P-2023-09-05 | PacWave24 Exercise Draft Summary Report will be shared with Member States 10 days prior to ICG/PTWS-XXXI | ICG/PTWS-XXX | TT-PW/Sec | 2025-03 |  | IN PROGRESS
P-2023-09-06 | PacWave24 Summary Report will be published and posted at www.pacwave.info on 30 June 2025 | ICG/PTWS-XXX | TT-PW/Sec | 2025-06 |  | NOT STARTED
P-2023-09-07 | Initiate preparedness for ICG/PTWS-XXXI | ICG/PTWS-XXX | Dakui Wang/Sec | 2024-03 |  | IN PROGRESS
P-2023-09-08 | Initiate preparedness for ICG/PTWS-XXXII | ICG/PTWS-XXX | TNC France/Sec | 2025-03 |  | NOT STARTED
P-2023-09-09 | Organize a scientific meeting of experts on the New Hebrides Trench | ICG/PTWS-XXX | WG1/Sec | 2025-03 |  | IN PROGRESS
P-2023-09-10 | Change the PTWS Earthquake Source Zone map in TS 130 to reflect the expansion of the PTWS Earthquake Source Zone to include an area from 63°S to 52°S and from 72°W to 18° W to include the Scotia Arc and its adjacent seismic zones. | ICG/PTWS-XXX | Chair/Sec | 2024-09 |  | CANCELED | Recommendation not approved at the EC-57.
P-2023-09-11 | Write to Member States to request feedback on the proposed changes to Telefax messaging, and also request Member States to indicate whether the proposed changes pose an unacceptable risk to their respective NTWCs and, if so, recommend those Member States work with their TSP to identify alternative methods for receiving TSP messages. | ICG/PTWS-XXX | WG2/Sec | 2024-03 |  | NOT STARTED
P-2023-09-12 | Agrees that PTWC implement some changes to its text products (putting the names of countries and territories with a potential threat in alphabetical order, organising the list of expected and observed tsunami arrival times by country and territory, including an indicator for the type of observation made, and replacing the term “height” with “amplitude” which is more appropriate) following notification to Member States by circular letter three months in advance in accordance with the change process put in place by ICG/PTWS-XXVI in 2015. | ICG/PTWS-XXX | PTWC | 2024-03 |  | IN PROGRESS
P-2023-09-13 | Rename the forecast category labeled “less than 0.3 meters” and replace it with the label “no threat” indicates a level of danger rather than just the tsunami amplitude | ICG/PTWS-XXX | PTWC | 2024-03 |  | IN PROGRESS
P-2023-09-14 | PTWC to finalize necessary preparations to provide special tsunami maritime safety products specifically for ships for all NAVAREA Coordinators in the Pacific and in the Southwest Atlantic (e.g. NAVAREAs VI, X, XI, XII, XIII, XIV, XV, and XVI) to transmit to the NTWCs to be forwarded to the NAVAREA Coordinators of their countries, or upon their request directly to the NAVAREA Coordinators in the absence of a NTWC. | ICG/PTWS-XXX | PTWC, Sec | 2024-09 |  | DELAYED
P-2023-09-15 | Requests the PTWS Steering Committee to finalise its decision at its next meeting on the provision of tsunami maritime safety products for a period of testing to be followed by a full operational implementation by the PTWC in 2024-2025. | ICG/PTWS-XXX | SC | 2024-03 | 2024-03 | COMPLETED
P-2023-09-16 | WG3 develop formal guidance for ICG/PTWS on the application of the proposed Tsunami Ready Equivalency Approach, led by WG3 TT on Tsunami Ready, in consultation with Regional Working Groups. | ICG/PTWS-XXX | WG3/TT-TR | 2025-03 |  | IN PROGRESS
P-2023-09-17 | Present Global Performance Monitoring Framework at the next TOWS-WG for endorsement of the global adoption by all ICGs | ICG/PTWS-XXX | TT-TWO PTWS Reps | 2024-02 |  | DELAYED
P-2023-09-18 | TOWS-TT-DMP to work with the IOC Tsunami Unit to develop Global Performance Monitoring Framework web portal | ICG/PTWS-XXX | TT-DMP Reps, TSR | 2024-12 |  | IN PROGRESS
P-2023-09-19 | Admit the start of the official full functional operations of CATAC, starting after the IOC governing body meeting in 2024, with the specific starting date to be decided after the coordination with the ICG/CARIBE-EWS | ICG/PTWS-XXX | ICG | 2025-06 |  | IN PROGRESS | In the ICG/CARIBE-EWS XVII session, the ICG/CARIBE-EWS recommended the consideration of CATAC as a TSP in its XVIII Session in 2025 to enable the IOC Assembly to consider the final admission of CATAC as TSP in June 2025
P-2023-09-20 | ITIC to pilot the PTWS Minimum NTWC Competency Framework through the development and conduct of a training course during the intersessional period, and report back on its outcome to the Thirty-first Session of the ICG/PTWS | ICG/PTWS-XXX | ITIC | 2025-04 |  | IN PROGRESS
P-2023-09-21 | ICG/PTWS WG2 to report on the use of the PTWS Minimum NTWC Competency Framework by Member States during the intersessional period to the Thirty-first Session of the ICG/PTWS | ICG/PTWS-XXX | WG2 | 2025-04 |  | IN PROGRESS
P-2023-09-22 | Strengthen the mandate and ability of the Steering Committee to deliver on the Ocean Decade goals | ICG/PTWS-XXX | PTWS/SC | 2024-03 |  | DELAYED
P-2023-09-23 | Develop an online survey of warning and mitigation capabilities in the Pacific Island Countries and Territories (Member countries and IOC). | ICG/PTWS-XXX | WG-PICT-TT-CD | 2025-03 |  | IN PROGRESS
P-2023-09-24 | WG2/TT-TGV develop guidelines on SOPs to monitor, detect, warn, and prepare for any volcano-induced tsunami waves. | ICG/PTWS-XXX | WG2/TT-TGV |  |  | NOT STARTED
P-2023-09-25 | WG2/TT-TGV develop guidelines on SOPs to monitor, detect, warn, and prepare for any volcano process that could induce tsunami waves. | ICG/PTWS-XXX | WG2/TT-TGV |  |  | NOT STARTED | Reflected in the Executive Summary and noted by the EC-57.
P-2023-09-25 | Among the volcanoes with potential tsunami threat, to identify those with implemented tsunami hazard assessment, monitoring, warning, and preparedness systems. | ICG/PTWS-XXX | WG2/TT-TGV | 2025-03 |  | NOT STARTED
P-2023-09-26 | To establish direct collaboration between ICG/PTWS member states and IAVCEI to facilitate the contribution of PTWS tsunami expertise to the monitoring and warning capability of existing volcano monitoring centres or NTWCs, as appropriate. | ICG/PTWS-XXX | WG2/TT-TGV | 2025-03 |  | IN PROGRESS | Through the CL-3029 issued on 14 February 2025, efforts are in place to bring the stakeholders together for akk ICGs through which PTWS will also benefit.
P-2023-09-27 | To Identify potential volcanic partners in countries and international bodies, and recommend collaboration opportunities with them to improve tsunami early warning and to support the downstream decision makers affected by the volcanically-generated tsunami. | ICG/PTWS-XXX | WG2/TT-TGV | 2025-03 |  | IN PROGRESS
P-2023-09-28 | WG2/TT-TGV develop guidelines on SOPs to monitor, detect, warn, and prepare for any volcano process that could induce tsunami waves. | ICG/PTWS-XXX | WG2/TT-TGV | 2025-03 |  | NOT STARTED
P-2024-03-01 | Organize a SC Meeting in Honolulu in September | SC Meeting 2024-03 | Chair, TS, ITIC | 2024-09 | 2024-09-01 | COMPLETED
P-2024-03-02 | Secretariat to describe approval of the NTWC Competency Framework in the Executive Summary and the Summary Report of the ICG/PTWS-XXX Session | SC Meeting 2024-03 | TS | 2024-09 | 2024-06 | COMPLETED
P-2024-03-03 | Conduct the trial dissemination of the dummy message from the PTWC to the NAVAREA coordinators through the NTWCs during the Pacific Wave 24 | SC Meeting 2024-03 | PTWC | 2024-11 | 2024-11-01 | COMPLETED
P-2024-03-04 | TSPs to begin to edit/revise the Users’ Guide according to the common structure | SC Meeting 2024-03 | CATAC, NWPTAC, PTWC, SCSTAC | 2025-04 |  | IN PROGRESS
P-2024-03-05 | Regional WGs to consider updating their ToRs to include SMART Cable. | SC Meeting 2024-03 | Regional WGs | 2025-04 |  | IN PROGRESS
P-2024-03-06 | Nominate PTWS representatives for the IOC/UNESCAP Tsunami Capacity Assessment Project | SC Meeting 2024-03 | Chair | 2024-09 | 2024-09-01 | COMPLETED | Initial nonimations for the UNESCAP Workshop in Thailand (4-6 September 2024) has been made. Final decision is expected at the SC Meeting in Hawaii. Ms. Lara Brand and Dr. Laura Kong are representatives for the TCPA.
P-2024-06-01 | Actively engage with Argentina regarding Argentinian Search and Rescue (SAR) and NAVAREA VI coordination responsibilities. | EC-57 | Chair, TS, ITIC | 2025-04 |  | NOT STARTED
P-2024-07-01 | Request the Chair to send an endorsement letter to UNESCAP regarding PTWS involvement in the Phase II of the IOC/UNESCAP Tsunami Capacity Assessment Project | UNESCAP Meeting on 23.7.2024 | Chair, TS | 2024-09 | 2024-09 | COMPLETED
P-2024-09-01 | Request the Chair to send an endorsement letter to UNESCAP regarding PTWS involvement in the Phase II of the IOC/UNESCAP Tsunami Capacity Assessment Project | UNESCAP Meeting on 23.7.2024 | Chair, TS | 2024-09 | 2024-09-01 | COMPLETED

## OVERVIEW
PTWS ACTION MONITOR OVERVIEW
2025-04-07 | COMPLETED | IN PROGRESS | DELAYED | FAILED | NOT STARTED | CANCELED | TOTAL
# | 11 | 15 | 3 | 0 | 8 | 1 | 38
% | 28.9474 | 39.4737 | 7.8947 | 0 | 21.0526 | 2.6316 | 100